## Sheet1
Schedule
Month | Day | Tasks | Features
February | 5 | Setup the webserver. Implement a basic test webpage. Research Watson AI system. | The user can navigate to a basic test page.
| 12 | Implement the signup feature. | The user can signup for the service provided that they have a penn state user account.
| 19 | Import information from the student directory into the user accounts. Implement the account details page. | The account details page includes information obtained from the student directory.
| 26 | Implement the basic login feature. | The user can login to the service provided that they had used the signup feature. The email address field must match the email address of a user account and the password field must match the password of the user account.
March | 5 | Nothing. Spring Break.
| 12 | A simple clustering algorithm using the AI (e.g. what are the important factors for providing recommendations?) | A simple program matching individuals within a data set.
| 19 | Modify the account details page. | The user can make changes to their user account.
| 26 | Implement the friends page. | The user can add and remove friends from their account.
April | 2 | Implement the recommendations page. | The recommendations page lists all available user accounts.
| 9 | Implement the AI service to provide recommendations on the recommendations page. | The recommendations page lists user accounts with similar attributes; these attributes should be listed with each user account.
| 16 | Implement SSL on the webserver to protect communications. | The website is served via an HTTPS connection as indicated by most web browsers.
| 23 | Identify and fix defects. | The final product works as described in the functional requirements.
| 30 | Build a promotional website. | The user can navigate to the promotional webpage. The promotional webpage links to the signup page.